Scientific overview

regarding the implementation of the project during

October 2011 – December 2014

Written heritage of the Roman civilization in northern Romania

project number PN-II-ID-PCE-2011-3-0096

The aim of the current project is the valorization and in some cases - not necessarily very few – the scientific and cultural recovery of the epigraphic heritage of northern Romania (the territory of Dacia Porolissensis). The period 2011-2014 overlaps Objectives 1-3; these and the related activities were carried on in good conditions, with some adaptations and adjustments imposed by objective reasons.

THE OBJECTIVES

O1. Collecting the edit epigraphic material from Dacia Porolissensis

This objective, which had originally been allocated to 2011, was also conducted during the subsequent years, due to the great mass of literature involved and to the need of finding adequate and effective methods of information systematization.

A1. Organizing bibliographic material and documentation

A first step initiated in this stage is organizing the already existent material (more specifically, files on inscriptions from Dacia Porolissensis made and collected in recent decades by the PL, prof. Ioan Piso.) These records were important in the early stages of our research, as they comprise both museological information (inventory number, storage location - of course, it has not remained unchanged in most cases) and bibliographic data, photographs, drawings, some proposals for reading the inscriptions, etc.. Even if they are only drafts, we considered them relevant as early instruments  and carried on their organization and digitization.

The inscriptions from Dacia Porolissensis were divided into three categories, which will coincide with the three volumes of the final monograph: the first, having Porolissum as central point,  deals with the findings from the limes; the second focuses on the area around the center of the province and Napoca; and the third is considering geographical localities that are to be connected to the urban center of Potaissa.

With this division of the province in mind, the team members began collecting existing bibliography for each inscription known. The accumulation of bibliography was based on two distinct components, namely collection of edit works and accessing electronic sources. Regarding "traditional" bibliography, it turned out to be multifolded and varied for most of the inscriptions. Thus, we have extensively documentated inscriptions, reported, for example, by J. F. Neigebaur, M. J. Ackner and F. Müller, subsequently published in CIL, revised by the Hungarian archaeologists who were interested in antiques in Transylvania in the late nineteenth century and early twentieth century (G. Téglás, G. Finaly, Á. Buday etc.), and then repeated in various contexts by researchers of the twentieth century. As a detail, the three manuscripts of Mezertius were identified in the Bibliotheca Vaticana and copied; the research of these manuscripts is obviously of great interest not only for the present project, but also for studying epigraphic pieces from other regions of Dacia. Other parts - and not necessarily very few - are discoveries made more or less recently, in the interwar period until recent years. The latter have the great advantage of a more accurate bibliographic context of discovery, but in cases of re-discovery ("wandering stones", identified only in recent decades), there is a disadvantage. Several pieces from Potaissa (Turda) were identified within a broad research action in the deposits Institute of Archaeology "Vasile Parvan" from Bucharest, and hundreds of tegular stamps from National History Museum of Transylvania, Cluj Napoca, were identified, photographed and processed.

The main electronic resources used was the Epigraphische Datenbank coordinated by the University of Heidelberg, Ubi erat Lupa and Epigraphik Datebank Clauss/Slaby. But these serve mainly to register bibliographic references, as databases provide only a single reading of the inscription and partial bibliography. The electronic resources mentioned above have proved extremely useful especially through the photographic material provided.

A2. Mobilities and bibliographic documentation

This activity proved to be continuous during the last years, as new discoveries implied documentation and constant reference checking. A significant part of the bibliography of each inscription was found in libraries in Cluj-Napoca (approx. 70% of the total), and some of the pieces were photographed in the Cluj Napoca history museum deposits. In order to complete bibliographic documentation, as well as taking pictures, the researchers involved in the project have undertaken several internal (Zalău, Bucharest; Caransebeș, Alba Iulia, Timișoara, Dej, Bistrița, etc.) and external mobilities (Vienna, Budapest, Heidelberg, Berlin). They have proved useful not only in the strict register of collecting bibliography, but also in identifying possible analogies and in placing particular reality in a more general context.

O2. Processing and analyzing the collected material

This objective overlapped the collection of information described at O1. Also, for producing some of the articles, extensive research was undertaken, involving an important aspect of conceptualization.

A1. Field research

This activity overlapped sometimes O1.A2., as bibliographic documentation is sometimes accompanied by proper analysis of the material.

A2. Office research

The analysis undertaken in this activity were varied and extensive, and they are mainly visible in the articles, studies and books published by the team members. We will not linger only on the main aspects and the importance of such research.

The intrinsic analysis of the inscriptions was based on an inscription sheet, developed for eac monumnet. The structure is: identification description (type of inscription, stylistic data, conservation status); writing (ligatures, letters sizes); conditions of discovery; storage place; bibliography; Latin text, in diplomatic transcription; translation; epigraphic and historical interpretation; dating; photo / drawing. Presently, we have about 1000 complete imscription sheets and the raw material for 500 more during the first months of 2015.

An interesting component of research overlapped an old scientific interest of the PL. Thus, a series of petrographic analyzes undertaken on pieces of marble, was integrated into a multidisciplinary research across the province; the archaeological part was provided by Ioan Piso, and the mineralogical studies by Harald Schwaighofer and Bernd Müller from Vienna and Marcel Benea from UBB. The result was the volume Der Marmor in römischen Dakien. Samples were taken from all known marble quarries in Dacia, as from the representative pieces in museums. These samples were analyzed at the University of Vienna. Among the conclusions of the paper was that large parts, eg the architectural and large inscriptions were made of local Bucova marble, while smaller and more demanding artifacts, such as votive plaques or small statues were generally made of Greek marble (Thassos, Naxos, Paros) or Micro Asian one (Prokonnesos). The catalog includes over 100 pieces, many of which come from northern Dacia.

A3. Database online

The web platform was one of the problems of faced by the team, as this form of dissemination via Internet proved to be only partially achieveable. The project benefits from a site, the information, data and contact details are, online but loading the material to be published is not possible (the volumes will be published in the prestigious publishing Diffusion de Boccard, Paris and reducing their impact through accessibility is not acceptable for the publishing house). However, being aware of the importance of dissemination in the virtual environment, we tried to make available at least some of the results, as seen on the project site.

A4. Dissemination

For clarity, dissemination will be discussed globally at the end of this scientific report.

O3. Completion of research

Given the budget cuts of 2013 and 2014, this objective was not fullfilles, as it implies the complete fullfillement of the other two objectives

A1. Processing the results

The main result were published as parts of various studies and article, some bringing forth major information. For example, after studying the construction inscription of the fort Pomet (Porolissum), we found that the stone phase was not built under Caracalla (112-117), but under Hadrian. Studying inscriptions from Napoca, clarifications were brought forth on the location of the praetorium of the financial procurator of Dacia Porolissensis (Studia Porolissensia III, by I. Piso). A recently discovered inscription from Jebucu (County. Salaj) was studied in detail by R. Ardevan and R. Zagreanu (Eine von Jebucu Römische Inschrift (Salaj Kreis)), and the results provide important data on epigraphic culture of this area of Dacia. It was revealed the major role of the lapidary workshops from Napoca, being a model for masons in smaller, rural settlements, but more importantly, this inscription proves the existence of the village Rucconium its vicus status.

One of the most important results was the reintepreting a Potaissa inscriptions (I. Piso, Studia Porolissensia IV) , which revealed the name of emperor Aemilius Aemilianus. Since the inscription is dedicated to Marcus Publicianus Rhesus (the cognomen is the Thracian), prefect of the ala I Batavorum and agens vice praefecti legionis V Macedonicae, dating the inscription during the short reign of Aemilianus is extremely important, thus pre-dating the reform of Gallienus and proving that the latter's initiative to focus military power in the hands of the equites was the last step of a longer evolutionary process. Thus, this discovery is important for the history of the Roman Empire and truly transcends provincial research.

R. Ardevan’s study Die Entwicklung in zwei Militärsiedlungen kulturelle Norddakiens, Gherla und Ilişua: ein Überblick vergleichender followed closely cultural events - noticeable not only by epigraphic sources (language, script, aspect of monuments, churches, birthday etc.) – in two military settlements in Dacia Porolissensis, with surprising results; despite the many similarities between them, they present different cultural aspects, differences expressing colonization phenomenon, evolution, specific social, acculturation etc. This fact illustrates convincingly that provincial society was much more complex and varied than previously thought.

Beyond these approaches, 2014 also saw the publication of two monographs, signed by Rada Varga and George Cupcea. The former considers the peregrines (about 10% from the characters attested in the province) from Dacia, while the latterfocuses on the professional ranks of the Roman army from the same province. Of course, both monographs benefitted, on the one hand, from the material collected for Dacia Porolissensis, and on the other hand, both offer a new light on the realities of the province affected by the project.

A2. Developping the monograph

Given the budget deficit, this activity is ongoing, as documentation, mobilities, drawings, etc. are still to be made during the next year.

A3. The official launch of the site

We can say that this work went into that category initially unforeseen risks inherent in any project with medium and long lasting way. Given the editorial rigors already mentioned, the official website was re-thought, but is was launched at the end of 2011 and constantly updated.

A4. Dissemination

Dissemination will be discussed in the next section of the report.

DISSEMINATION

As an important component of the overall economy of the project, we chose to treat dissemination separate - although of course, both in terms of achievement and de facto, it was inherent in each goal.

Given that all the results are detailed on the project website (http://hiphi.ubbcluj.ro/written_heritage/), where full references are available and in most cases the text contribution, we present hereinafter a graph summarizing the scientific results reported:

CONCLUSIONS

Considering all of the above, we conclude that the objectives for 2011-2014 were successfully met, even under the 2013-2014 budget cuts and the recorded minuses are easily recoverable by proper funding in 2015. At this point, we can say without a doubt that the final results of this project will be highly relevant to the scientific community.